## Sheet1
Id | Back/Front | Where? | Description | Type | Status | LastUpdateBy
1 | Backend | Advertiser | Search by Status not working (Enum's bug) | Bug | Not fix | Cá
2 | Backend | Advertiser | Create New | Undone function | Not fix | Cá
3 | Backend | Customer | Edit button | Bug | Not fix | Cá
4 | Backend | Customer | Sort by Status not working (Enum's bug) | Bug | Not fix | Cá
5 | Backend | Merchant | Sort By Scale show wrong out put | Bug | Not fix | Cá
6 | Backend | All SeedData | Some entity, DateCreated and DateModified weren't seeding | Dunno | Not fix | Cá
7 | Backend | Button Save | Wrong position | Bug | Not fix | Cá
8 | Backend | Merchant | Sort by Status not working (Enum's bug) | Bug | Not fix | Cá
9 | Backend | Merchant | Delete not working | Bug? | Fixed | Cá
10 | Backend | Merchant | Create New | Undone function | Not fix | Cá
11 | Backend | WebMaster | Sort by Position not working | Bug | Not fix | Cá
12 | Backend | WebMaster | Sort by Status not working (Enum's bug) | Bug | Not fix | Cá
13 | Backend | WebMaster | Create New | Undone function | Not fix | Cá
14 | Backend | WebMaster | Edit button | Bug | Not fix | Cá
15 | Backend | WebMaster | Delete not working | Bug? | Fixed | Cá
16 | Backend | AdPosition |  | Undone function | Not fix | Cá
17 | Backend | Invoice | Delete Customer => Delete all the ralate Invoice | Bug? | Fixed | Cá
18 | Backend | InvoiceDetail | Delete Customer => Delete all the ralate InvoiceDetail | Bug? | Fixed | Cá
19 | Backend | Delivery | Delete Customer => Del all the Delivery | Bug? | Fixed | Cá
20 | Backend | AdContract |  | Undone function | Not fix | Cá
21 | Backend | User | Add col "Loại" but can't load the FKNavigation data, don't know how | Undone function | Not fix | Cá
22 | Backend | Delivery | M-Update status and update totalprice | Undone function | Not fix | Cá
23 | Frontend | Delivery | After Customer order successfully > create Delivery: status: Unconfirm, Ship = 0, TotalPrice=0. calculate OrderPrice plz. | Undone function | Not fix | Cá
24 | Backend | Delivery | Add UpdateStatus function (Select oneway_clientside) | Undone function | Fixed | Cá